N8N Sales AI Agent

AI Engineer Production Delivery Roadmap

Derived from the canonical PRD, Architecture & Epics ? ordered by current state and production gates (Revalidate ? Approve ? Integrate ? Pilot)

8 Gated Stages  ?  30 Work Items  ?  Each with Description & Definition of Done

Planning Rule: This is a stage-gate roadmap, not a committed sprint plan. A stage is committed only after its Entry Gate, start/end dates, available team capacity, and named accountable owner are recorded. None is currently committed; missing production dependencies remain Blocked.

Current State: The synthetic-local seven-workflow/PostgreSQL baseline has historical PASS evidence. It is revalidated in Sprint 1 rather than rebuilt; production Meta, LLM, CRM/Handoff, managed infrastructure, legal/privacy, and named ownership remain external gates.

Product Boundary: PostgreSQL owns durable business state; n8n orchestrates; the LLM drafts/classifies; deterministic Sales Policy and humans own commercial authority. ready_for_handoff is not closed_won, and Human-Owned suppresses automated replies and Follow-Ups.

Commitment Status: Stage 1 is the only commitment candidate after dates, capacity, and a named owner are supplied. Stages 2?7 remain gated backlog; Stage 8 is a pilot gate. The first implementation candidate is Story 1.1 only, and it still requires explicit approval.

# Stage 1 : "Synthetic-Local Baseline Revalidation"

Stage Goal: Confirm what is already delivered and produce current evidence before planning new implementation.

Entry Gate: Docker Desktop is available; the canonical planning pack and repository baseline are unchanged or their differences are understood.

Accountable Role: AI Engineer, with Quality Advisor review.

Exit Evidence: A current baseline map and reproducible local test report; no production-readiness claim.

## Task 1 : "Map the delivered baseline to canonical stories"

Description: Inventory the existing seven n8n workflows, ten typed configuration files, PostgreSQL state model, release manifest, and test harness; map each delivered capability to the canonical Epic/Story and requirement IDs.

Points of Done (Definition of Done):

- Every baseline capability is classified as Done, Needs Revalidation, Gap, or Blocked.

- Each Done item cites its repository artifact and evidence date.

- Synthetic-local proof is clearly separated from production proof.

- Previously delivered work is not scheduled for reimplementation unless a current check fails.

- The planning README and canonical epics remain the implementation authority.

## Task 2 : "Re-run the one-command synthetic-local evidence"

Description: Start the persistent local stack and run the authoritative repository harness against a reset synthetic environment, retaining the runtime only after the checks finish successfully.

Points of Done (Definition of Done):

- The harness completes S01-S26, concurrency/race checks, workflow identity checks, release-hash checks, and secrets hygiene checks.

- The full suite passes twice consecutively or the sprint remains open with the failing scenario IDs recorded.

- Generated plaintext is cleaned and no secret is added to source, exports, fixtures, or the report.

- The evidence records the actual n8n/PostgreSQL versions, date, command, result, and owner.

- The report states that real Meta, LLM, CRM/Handoff, and managed-infrastructure behavior is not proven.

## Task 3 : "Publish the baseline status and gap register"

Description: Convert the revalidation result into one short execution register showing what may proceed, what needs repair, and what is blocked by a production decision or external asset.

Points of Done (Definition of Done):

- Every planned item has a status, accountable role, dependency, and evidence link.

- Gaps are mapped to the existing canonical stories rather than duplicated as new authority.

- The release manifest remains livePromotionAllowed=false.

- No production integration task is marked Ready before its owning contract is approved.

# Stage 2 : "Production Decisions & Contract Freeze"

Stage Goal: Turn unresolved commercial, compliance, provider, and operating decisions into approved versioned inputs.

Entry Gate: Stage 1 evidence is current and the Executive Sponsor accepts the single-pilot boundary.

Accountable Role: Product Owner / Executive Sponsor; engineering supplies feasibility evidence but does not invent business decisions.

Exit Evidence: Approved decision register and versioned production contracts, each with owner and decision date.

## Task 1 : "Assign decision owners and freeze the pilot boundary"

Description: Resolve the canonical open-question register and define one bounded pilot: one approved WhatsApp asset, one offer family, one language set, one market/jurisdiction, and one explicit volume cap.

Points of Done (Definition of Done):

- All twelve canonical open decisions have an owner, status, decision date, and affected release gate.

- Pilot scope names the WhatsApp asset, offer family, language(s), jurisdiction, operating hours/timezone, and maximum concurrency/volume.

- Any undecided launch-blocking item keeps the affected production path Blocked.

- Multi-tenant, multi-market, multi-offer, and unrestricted-language expansion remain outside MVP.

## Task 2 : "Approve commercial and content authority contracts"

Description: Approve the Product Knowledge and Sales Policy ownership model, offer catalogue, pricing/tax fields, prohibited claims, escalation taxonomy, publication roles, effective dates, and rollback authority.

Points of Done (Definition of Done):

- The approved Product Knowledge and Sales Policy contracts use typed fields and versioned source references.

- The Assistant may present only the approved list price or explicitly approved fixed offer.

- The LLM has no authority to negotiate, approve contracts, create binding terms, or record closed_won.

- Authors, approvers, publishers, revokers, and rollback actors are named by role.

## Task 3 : "Approve messaging, consent, and customer-rights rules"

Description: Approve Meta assets/templates, consent evidence, opt-out wording/signals, bot disclosure, quiet hours, frequency caps, service-window behavior, after-hours wording, and launch-jurisdiction obligations.

Points of Done (Definition of Done):

- The consent/template register is versioned and tied to the approved WhatsApp asset and language.

- Opt-out precedence, complaint handling, explicit human-request handling, and deletion-request routing are approved.

- Only approved templates may be used outside the customer-service window.

- Legal/Privacy and Marketing Operations approvals are recorded with dates and evidence references.

## Task 4 : "Approve model, data, Handoff, and operating contracts"

Description: Select the production LLM, managed PostgreSQL service, CRM/Handoff destination, acknowledgement signal/SLA, escalation path, retention/deletion schedule, incident path, and named human sales coverage.

Points of Done (Definition of Done):

- The LLM decision records provider, model, region, retention/no-training terms, permitted payload, credential owner, and budget.

- The Handoff contract records assignment target, authenticated acknowledgement signal, SLA, timeout, after-hours, ambiguous-delivery, and permanent-failure behavior.

- The managed PostgreSQL decision records approved region, backup/PITR, restore owner, maintenance expectations, and connection limits.

- Retention/deletion, incident response, monitoring ownership, and pilot sales coverage are approved before Stage 3 exits.

# Stage 3 : "Production Security, Data & Release Foundation"

Stage Goal: Harden the existing local design for a governed production-like environment without changing its commercial authority boundary.

Entry Gate: All Stage 2 contracts required by a task are approved and versioned.

Accountable Role: AI Engineer with Security, Privacy, Database, and Operations owners.

Exit Evidence: Production-like infrastructure controls, deletion proof, n8n audit evidence, and a pinned non-live release candidate.

## Task 1 : "Production config validation & approval-aware activation"

Description: Extend the existing immutable config publication and activation path only where the approved production contracts require stricter validation, authorization, effective-time, or rollback behavior.

Points of Done (Definition of Done):

- Existing schemas and activation logic are reused; no second configuration system is created.

- Unknown fields, invalid commercial values, unsupported language/template references, missing approval evidence, and overlapping effective dates are rejected with actionable errors.

- Only an authorized approver can activate or roll back a production version; upload never activates implicitly.

- Every publish, activation, rejection, revocation, and rollback is auditable.

- An existing approved internal surface is used unless a separate dashboard is explicitly approved.

## Task 2 : "Managed PostgreSQL controls & privacy lifecycle"

Description: Deploy the existing business-state model to the selected managed PostgreSQL service and implement the approved retention/deletion lifecycle across every in-scope store and reference.

Points of Done (Definition of Done):

- TLS, least-privilege roles, pooling/connection limits, backup/PITR, metrics, patched version, and approved region are verified.

- Migration runs cleanly on a fresh production-like database and is idempotent where designed.

- A restore drill records recovery result, environment, owner, and unresolved RTO/RPO decisions.

- A Contact deletion request removes or irreversibly anonymizes in-scope data while retaining only approved minimal audit evidence.

- Deletion, retention expiry, legal hold, and failed deletion attempts are tested and audited.

## Task 3 : "n8n hardening, secrets, and access controls"

Description: Harden the selected n8n deployment using pinned supported components, least privilege, restricted editor access, reviewed native nodes, network controls, and approved secret storage.

Points of Done (Definition of Done):

- Production credentials exist only in approved secret stores/n8n credentials and never in prompts, exports, fixtures, source control, or execution logs.

- The production node allowlist, SSRF protection, outbound egress rules, editor/admin access, and execution-data settings are documented and verified.

- Community/custom nodes are absent unless separately reviewed and approved.

- The n8n security audit has no unapproved finding and its evidence owner is recorded.

## Task 4 : "Pinned promotion and rollback foundation"

Description: Extend the existing release manifest so a production-like candidate pins every proven applicable workflow, migration, schema, policy, knowledge, prompt, model, template, image/package version, and test-evidence reference. External provider API versions remain pending_external_proof until credentialed Stage 4 checks establish them.

Points of Done (Definition of Done):

- Manifest generation is reproducible and canonical hashes match the reviewed artifacts.

- Ordered migrations run before compatible workflows activate.

- Rollback uses a compatible forward-safe procedure; destructive schema reversal is not assumed.

- Promotion, rollback, kill-switch state, and actor/reason are Audit Events; unproven external provider versions are recorded as pending_external_proof or not_applicable, never guessed.

- livePromotionAllowed remains false until an authorized Release Owner records every required approval and the proven provider versions are pinned.

# Stage 4 : "Production Integration Adapters"

Stage Goal: Connect approved external systems to the existing persisted-intent and state-transition contracts without sending to real customers.

Entry Gate: Selected Meta, LLM, CRM/Handoff, managed PostgreSQL, secret-store, and test-environment assets are available.

Accountable Role: AI Engineer with each external-system owner.

Exit Evidence: Credentialed connectivity and contract tests in isolated test assets; no uncontrolled customer message.

## Task 1 : "Meta integration in three independently gated story slices"

Description: Deliver Story 1.1 trusted ingress first, then Story 1.4 dispatch, then Story 1.5 provider-status reconciliation. Each slice requires its own approved contract and evidence; later slices are not implied by approval of ingress.

Points of Done (Definition of Done):

- Slice 1.1: webhook verification, strict raw-body signature validation, whole-envelope identity checks, bounded input, PII-minimized rejection audit, ordered persistence, and one response per envelope pass.

- Only the approved test asset is accepted and test/production isolation is proven; local generated credentials remain protocol proof, not credentialed Meta evidence.

- Slice 1.4: only after separate approval, outbound sends reuse the unique persisted intent and record the provider message ID without blind resend on ambiguous outcomes.

- Slice 1.5: only after separate approval, duplicate/replayed and out-of-order status callbacks converge on immutable evidence and one derived state.

- Each slice fails closed, remains independently runnable, and blocks its dependent slice when authentication, throttling, timeout, database, identity, or connectivity checks fail.

## Task 2 : "Production LLM typed draft integration"

Description: Connect the approved LLM to the existing orchestrator so it receives an allowlisted bounded context and returns an untrusted typed draft/classification for deterministic validation.

Points of Done (Definition of Done):

- Provider, model, prompt, output schema, evaluation corpus, and result hash are pinned.

- The model receives only approved minimum data and no credential, hidden operational secret, or cross-Contact context.

- Invalid structure, missing sources, low confidence, policy conflict, timeout, or provider failure fails closed to approved clarification or Handoff.

- The LLM cannot send messages, invoke commercial side effects, approve terms, or write closed_won directly.

## Task 3 : "CRM/Handoff adapter transport & acknowledgement integration"

Description: Implement only the selected adapter transport, unique Handoff notification intent, authenticated acknowledgement, timeout, and failure contract. Representative claim/transcript/outcome operations remain Stage 6 work.

Points of Done (Definition of Done):

- One committed Handoff creates or reuses one notification intent with minimum required evidence and a least-privilege transcript reference.

- Acknowledgement is authenticated, correlated, idempotent, and never returns the Conversation to AI-Owned implicitly.

- Timeout, ambiguous delivery, retry exhaustion, after-hours, and permanent failure follow the approved escalation contract once.

- Only the CRM/human-owned path may record closed_won or closed_lost; ready_for_handoff is not closed_won.

- Outbound document automation is not added; representatives use the approved existing process after Handoff.

## Task 4 : "Credentialed connectivity & contract evidence"

Description: Provide the smallest safe smoke and contract checks proving each approved adapter can authenticate, exchange its test/no-op payload, reject invalid inputs, and fail closed without reaching a real customer.

Points of Done (Definition of Done):

- Meta, LLM, managed PostgreSQL, and CRM/Handoff checks are independently runnable and identify the failing contract.

- No-op/test calls use isolated assets and cannot be mistaken for production approval.

- Credentials and customer data are redacted from logs, evidence, screenshots, and repository artifacts.

- A failed adapter check blocks dependent Stage 5 work.

# Stage 5 : "MVP Controlled Customer Journey"

Stage Goal: Prove one real test-customer journey from trusted ingress through grounded response or Human-Owned Handoff with no unauthorized commercial action.

Entry Gate: Stage 4 contract evidence passes and the Release Set contains approved happy-path, safety, and interruption cases.

Accountable Role: AI Engineer with Product Owner and Quality Advisor.

Exit Evidence: End-to-end test-asset evidence for ingress, answer, interruption, dispatch, status, and Handoff paths.

## Task 1 : "Trusted real ingress & ordered persistence"

Description: Accept an approved test message through the Meta webhook, acknowledge quickly, authenticate and normalize it, deduplicate/reconcile replay, assign Conversation order, and persist it before any model call.

Points of Done (Definition of Done):

- Webhook acknowledgement meets the approved provisional target and is measured separately from processing-to-send time.

- Malformed, oversized, wrong-asset, unauthenticated, duplicate, conflicting-replay, and out-of-order events have deterministic outcomes.

- Every accepted inbound event is persisted exactly once with account, Contact, Conversation, correlation, provider, and ordering references.

- No model call or customer-visible side effect occurs before trusted persistence commits.

## Task 2 : "Bounded context, grounded draft & Lead Facts"

Description: Load the active consent, Product Knowledge, Sales Policy, model/prompt/schema, and bounded Conversation history; produce a typed grounded draft and evidence-linked Lead Fact proposals.

Points of Done (Definition of Done):

- Context is scoped to one account/Contact/Conversation with no cross-customer leakage.

- Every factual claim and accepted Lead Fact cites an approved source or source customer message.

- Unsupported, conflicting, stale, or missing evidence produces clarification or Handoff, never invention.

- The decision records the exact policy, knowledge, prompt, schema, model, workflow, and source-message versions used.

## Task 3 : "Deterministic commercial gate & escalation detection"

Description: Run every model draft/classification through the deterministic policy gate and combine deterministic safety triggers with governed classification for buying intent, uncertainty, complaint, privacy/legal/safety risk, and frustration.

Points of Done (Definition of Done):

- Unapproved offer, price, discount, tax, term, claim, language, or action is blocked before an outbound intent exists.

- Explicit opt-out and human requests are deterministic high-precedence triggers, not model-only classifications.

- Low confidence, missing evidence, unsupported terms, buying intent, complaint, and safety/privacy/legal uncertainty fail closed to Handoff.

- The gate produces one typed outcome: approved response, safe clarification, suppression, or Handoff.

- No automated path can bind the company or record closed_won.

## Task 4 : "Authorized idempotent dispatch & reconciliation"

Description: Persist one unique outbound intent, claim it with a short lease, recheck every current authorization immediately before provider-call start, dispatch outside database locks, and reconcile provider outcomes safely.

Points of Done (Definition of Done):

- Concurrent workers and retries produce at most one logical customer-visible send.

- Opt-out, Human-Owned, kill-switch, stale Conversation version, revoked policy/knowledge, or expired authorization suppresses the send before provider-call start.

- A pre-call failure is safely retryable; ambiguous timeout or crash-after-call enters reconciliation rather than blind resend.

- Provider callbacks and reconciliation converge on the correct outbound intent and preserve unknown delivery states explicitly.

- Lease expiry, retry age/attempt limits, final failure, and Operations visibility are proven by test.

## Task 5 : "Opt-out/human interrupt & atomic Handoff transition"

Description: Honor opt-out or an explicit/mandatory Handoff at any stage by atomically changing database state, cancelling incompatible automation, creating/reusing one Handoff, and creating at most one approved transfer-acknowledgement intent.

Points of Done (Definition of Done):

- The database transaction sets Human-Owned, increments Conversation version, creates/reuses one Handoff, cancels pending automation, and records Audit Events.

- Provider delivery is not claimed atomic with the database; the acknowledgement is dispatched asynchronously through the unique outbox path.

- While Human-Owned, no automated reply or Follow-Up is permitted except the one precommitted fixed non-commercial transfer acknowledgement.

- Opt-out has higher precedence and suppresses even the transfer acknowledgement.

- Races between a generated reply and a later opt-out/human request always resolve through the final authorization check without an unauthorized send.

# Stage 6 : "MVP Follow-Up, Human Operations & Metrics"

Stage Goal: Complete compliant re-engagement and give authorized humans the minimum controls and evidence needed to operate the pilot.

Entry Gate: Stage 5 core journey passes and Sales Operations confirms coverage, SLA, escalation, and reporting definitions.

Accountable Role: AI Engineer with Sales Operations, Operations Owner, and Sales Analytics.

Exit Evidence: Follow-Up, Handoff operations, monitoring, pause, and reproducible KPI/counter-metric evidence.

## Task 1 : "Production Follow-Up eligibility & exactly-once scheduling"

Description: Extend the durable PostgreSQL Follow-Up path to apply the approved production consent, ownership, last-inbound, frequency, quiet-hours, campaign, and WhatsApp service-window/template rules immediately before send.

Points of Done (Definition of Done):

- Follow-Ups are durable records with due time, generation, Conversation version, and unique action key; no in-memory Wait node owns business state.

- Concurrent schedulers claim due work with a short lease and create at most one eligible outbound intent.

- Reply, opt-out, Human-Owned, campaign stop, stale version, frequency cap, quiet hours, or missing eligible template suppresses/cancels the job with a typed reason.

- Eligible content enters the same final authorization, dispatcher, provider-status, retry, and reconciliation path as other outbound intents.

- Tests cover reply-before-due, opt-out race, Human-Owned, window/template matrix, frequency cap, duplicate scheduler, and expired lease.

## Task 2 : "Representative operations on the approved Handoff adapter"

Description: Using the approved Stage 4 adapter contract, provide authorized representatives the minimum existing/internal surface needed to claim one Handoff, access its evidence-linked transcript, and record the final CRM-owned outcome.

Points of Done (Definition of Done):

- Concurrent claims allow exactly one authorized representative to win and record claim/acknowledgement time and SLA state.

- Transcript access is Contact-scoped, least-privilege, authenticated, expiring where applicable, and audited.

- The representative sees confirmed Lead Facts separately from unknowns and the applicable policy/offer references.

- CRM outcome sync is idempotent and only the authorized human/CRM path may record closed_won or closed_lost.

- No custom dashboard or arbitrary document-send endpoint is built unless separately approved.

## Task 3 : "Monitoring, alerting & global pause"

Description: Expose the minimum Operations queries/alerts for failed or ambiguous sends, stale Handoffs, stuck Follow-Ups, opt-outs, complaints, policy violations, backlog, and kill-switch state.

Points of Done (Definition of Done):

- Alerts have approved thresholds, target time, severity, owner, escalation route, and runbook reference.

- Global pause and scoped Conversation disablement stop new automated sends through the shared authorization path and are audited.

- In-flight/ambiguous actions remain reconcilable and no data is discarded when pause is enabled.

- A simulated failure spike, overdue Handoff, stuck Follow-Up, and policy-rejection threshold produce the expected evidence.

- An existing approved query/reporting surface is used unless a custom dashboard is explicitly required.

## Task 4 : "KPI & counter-metric reporting"

Description: Compute the approved Accepted-Handoff, response quality, cycle-time, Follow-Up revival, complaint/opt-out, duplicate-send, policy-violation, and cost measures against the approved baseline/control.

Points of Done (Definition of Done):

- Every metric has an approved numerator, denominator, eligibility rule, observation window, segmentation, and evidence owner.

- Measured values are separated from targets and unapproved assumptions.

- Running the report twice on the same immutable window produces the same result.

- ready_for_handoff is never counted as closed_won; final conversion remains CRM-owned.

- Management can review the approved report without direct production database access.

# Stage 7 : "Launch Readiness - Evidence & Release Control"

Stage Goal: Prove the release against approved safety, integration, load, recovery, privacy, security, and operational gates before any live activation.

Entry Gate: Stages 3?6 pass in the approved production-like environment and every launch-blocking owner is available for evidence review.

Accountable Role: Release Owner with Quality, Security, Privacy/Legal, Operations, Product, and Sales owners.

Exit Evidence: Versioned release reports, approvals, manifest hash, staging promotion, rollback drill, and explicit go/no-go record.

## Task 1 : "Versioned integration & adversarial Release Set"

Description: Execute the approved Release Set end to end across real test Meta, LLM, managed PostgreSQL, and CRM/Handoff assets, including grounded-answer and adversarial policy-bypass cases.

Points of Done (Definition of Done):

- The Release Set is versioned, labeled, independently reviewable, and pinned to provider/model/prompt/schema/policy/knowledge/workflow versions.

- Integration cases cover ingress, response, delivery status, opt-out, human request, Handoff acknowledgement, Follow-Up, and failure paths.

- Adversarial cases cover prompt injection, unauthorized price/discount/terms, source fabrication, hidden-instruction disclosure, cross-Contact access, tool/side-effect attempts, language switching, and post-Handoff automation.

- Zero critical policy violations occur; any critical failure blocks promotion regardless of aggregate pass rate.

- Reports record environment, result hash, owner, failure evidence, and approval.

## Task 2 : "Load, recovery, security & privacy evidence"

Description: Run the approved pilot-load, restart/recovery, ambiguous-provider, backup/restore, deletion, access-control, secrets, and n8n security checks against the production-like release candidate.

Points of Done (Definition of Done):

- Measured webhook-acknowledgement and processing-to-send p95 values are reported against approved provisional targets and pilot load.

- Restart, lease expiry, callback replay, provider ambiguity, and retry exhaustion preserve durable state with no unauthorized duplicate send or silent data loss.

- Backup restore and Contact deletion/retention evidence identify owner, environment, result, and unresolved RTO/RPO items.

- Security/privacy evidence covers least privilege, transcript isolation, node allowlist, SSRF/egress, secret redaction, model-payload allowlist, and approved retention/region terms.

- Any unapproved security, privacy, recovery, or data-loss finding blocks promotion.

## Task 3 : "Staging promotion, rollback & launch sign-off"

Description: Promote the manifest-pinned candidate to staging, exercise the compatible rollback procedure, run post-promotion/post-rollback reconciliation, and obtain the required go/no-go approvals.

Points of Done (Definition of Done):

- Promotion succeeds only when the candidate manifest hash matches the passed evidence set.

- Rollback is a single authorized controlled action, preserves data, avoids assumed destructive schema reversal, and is tested in staging.

- Post-promotion and post-rollback smoke/reconciliation checks pass before automation resumes.

- Product/Legal, consent, commercial, model, Handoff, privacy/security, operations, release, and pilot-volume gates have named approvals and dates.

- Only the authorized Release Owner may set livePromotionAllowed=true; a missing or failed gate leaves it false.

# Stage 8 : "Controlled Pilot Gate & Decision"

Stage Goal: Operate one capped live pilot safely, measure it against the approved baseline, and decide whether to stop, iterate, or plan a separate expansion.

Entry Gate: Stage 7 records an explicit go decision, live assets are isolated, human coverage is active, and rollback/kill-switch owners are present.

Accountable Role: Named Pilot Owner and Release Owner with daily Sales/Operations review.

Exit Evidence: Controlled smoke result, daily operating evidence, KPI/counter-metric report, incidents, and a recorded stop/iterate/continue decision.

## Task 1 : "Controlled production smoke & monitoring validation"

Description: Send approved controlled live messages through the production path and verify trusted ingress, grounded response or expected Handoff, provider status, monitoring, pause, and rollback readiness in real time.

Points of Done (Definition of Done):

- The smoke uses an approved test participant and cannot exceed the configured pilot cap.

- Expected Human-Owned Handoff and representative action count as valid behavior; the test does not require zero human intervention.

- Monitoring, correlation, alert delivery, Sales coverage, global pause, and rollback contacts are confirmed live.

- Any unexpected customer-visible behavior, unauthorized claim, privacy issue, duplicate send, or missing Handoff stops the pilot and invokes the approved response path.

## Task 2 : "Capped pilot activation & daily operations"

Description: Activate only the approved WhatsApp asset, offer family, language(s), jurisdiction, and volume/concurrency cap; operate with named daily review and immediate stop authority.

Points of Done (Definition of Done):

- Configuration cannot implicitly enable another offer, language, market, number, or authority dimension.

- Daily review covers Handoffs, failures/ambiguity, Follow-Ups, opt-outs, complaints, policy rejections, latency, cost, and data incidents.

- Sales coverage, acknowledgement SLA, after-hours path, Operations owner, complaint/block thresholds, and rollback criteria remain active.

- Every config change, pause/resume, incident decision, and release action is audited.

- The Assistant remains policy-bound; autonomous negotiation, binding terms, and autonomous closed_won remain prohibited.

## Task 3 : "Pilot outcome, continuation decision & post-pilot backlog"

Description: Compare the approved KPI and counter-metric results to the baseline/control, review qualitative Sales/customer evidence and incidents, and record a human-owned decision to stop, iterate, or propose a separate expansion plan.

Points of Done (Definition of Done):

- The decision cites the immutable measurement window, Release Set, incident log, cost, and evidence owners.

- Safety, consent, privacy, duplicate-send, complaint, and Human-Owned violations cannot be averaged away by conversion gains.

- Unmet targets produce an owned corrective action or stop decision, not an automatic scope expansion.

- Multi-offer, multi-language, multi-market, multi-tenant, custom dashboard/document automation, HA topology, and autonomous commercial authority remain post-pilot candidates only.

- Any proposed expansion starts with a new approved Product/PRD decision and enables one dimension at a time; no expansion code is built at this gate.